**G.SCHEDULES**

**SCHEDULE `F’ - REFERENCE TO GENERAL CONDITIONS OF CONTRACT**

**Name of work**: l Construction of Boundary Wall for the Additional Land of NIT Meghalaya at Sohra (Cherrapunjee)- Plot No. 263 & 264: Group-IV

|  |  |  |
| --- | --- | --- |
| 1. | Estimated cost of work | Rs 154.46 lakhs |
| 2. | Earnest Money | Rs 3,08,910.00 |
| 3. | Performance Guarantee | 5% |
| 4. | Security Deposit | 5% |

**General Rules & Direction:**

|  |  |  |
| --- | --- | --- |
| 1. | Officer inviting Tender | Director, NIT Meghalaya |
| 2 | Percentage on cost of materials and labour to cover all overheads and profits | 15% |
| 3. | Schedule of Rates (SOR) | DSR 2014 with applicable cost index. |

|  |  |
| --- | --- |
| **REF: CLAUSE 1 OF GCC: PERFORMANCE GUARANTEE** | |
| (i) Time allowed for submission of performance Guarantee from the date of issue of work order | 15 days |
| (ii) Maximum allowable extension beyond the period provided in (i) above | 15 days |
| **REF: CLAUSE 2A OF GCC: COMPENSATION OF DELAY** | |
| Authority of fixing compensation under clause 2A | Director, NIT Meghalaya |
| **REF: CLAUSE 5 OF GCC: TIME & EXTENSION FOR DELAY** | |
| Number of days from the date of issue of work order for reckoning date of start | 15 days |
| Time allowed for execution of work | 12months |

**TABLE OF MILE STONE (S)**:

***T= 15th day from the date of issue of work order.***

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Description of Mile stone (Physical)** | **Time allowed in days (from date of start)** | **Amount to be with held in case of non achievement of milestone** |
| **1.** | **Works upto ground level** | **T+3 months** | **Rs 80,000.00** |
| **2.** | **Works upto 1.2m from ground level** | **T+5 months** | **Rs 80,000.00** |
| **3.** | **Masonry work for full height above 1.2m** | **T+10 months** | **Rs 2,60,000.00** |
| **4.** | **Providing fencing on the top** | **T+11 months** | **Rs 50,000.00** |
| **5.** | **Finishing works** | **T+12 months** | **Rs 50,000.00** |
|  |  |  |  |

**REF: CLAUSE 6 & 6A OF GCC: MEASUREMENT OF WORK DONE AND COMPUTERIZED MEASUREMENT BOOK**

Clause applicable: 6/ 6A (Non applicable clause to be striked off)

**REF: CLAUSE 10A OF GCC: MATERIALS TO BE PROVIDED BY THE CONTRACTOR**

List of testing equipment to be provided by the contractor at site lab.

|  |  |  |  |
| --- | --- | --- | --- |
| 1 | Cube mould-4 nos | 4 |  |
| 2 | Sieve analysis apparatus-1 set | 5 |  |
| 3 | Dumpy level-1 no. | 6 |  |

**REF: CLAUSE 10 B (ii) OF GCC: MOBILIZATION ADVANCE, INTEREST & RECOVERY**

Whether Clauses 10 B (ii) shall be applicable: **No**

**REF: CLAUSE 12 OF GCC: DEVIATIONS/ VARIATIONS, EXTENT AND PRICING**

Deviation limit beyond which clause 12 shall apply

|  |  |
| --- | --- |
| For Superstructure Work | **25%** |
| For Foundation Work | **50%** |

**REF: CLAUSE 16 OF GCC: ACTION IN CASE OF WORK NOT DONE AS PER SPECIFICATION**

Competent Authority for deciding reduced rates: Director, NIT Meghalaya

**REF: CLAUSE 25 OF GCC: SETTLEMENT OF DISPUTES AND ARBITRATION**

Law court of Jurisdiction : Meghalaya High Court

**REF: CLAUSE 36 OF GCC: EMPLOYMENT OF GRADUATE/ DIPLOMA ENGINEERS**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Minimum qualification of Technical representative | Discipline | Designation (Principal Technical/ Technical representative) | Minimum experience | Number | Rate at which recovery shall be made from the contractor in the event of not fulfilling provision of clause 36 (i) |
| 1 | Graduate | Civil | Engineer | 3 years | 1 | Rs 25,000.00 |
| 2 | Diploma | Civil | Site Engineer | 3 years | 1 | Rs 15,000.00 |

**REF: CLAUSE 41 OF GCC: RETURN OF MATERIALS AND RECOVERY FOR EXCESS MATERIAL ISSUED.**

(i) Variations permissible on theoretical quantities:

|  |  |  |
| --- | --- | --- |
| (a) | Cement for works with estimated cost put to Tender not more than Rs. 5 Lakhs | 3% plus/minus |
| For works with estimated cost put to Tender more than Rs.5 lakhs | 2% plus/minus |
| (b) | Bitumen for all works | 2.5% plus only & Nil on minus side |
| (c) | Steel Reinforcement and structural steel sections for each diameter, section and category | 2% plus/minus |
| (d) | All other materials Nil |  |

(ii) Recovery rates for quantities beyond permissible variation:

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Description of Item** | **Rates in figures and words at which recovery shall be made from the Contractor** | |
| **Excess beyond Permissible variation** | **Less use beyond the permissible variation** |
| 1.  2.  3.  4.  5. | Cement  Steel reinforcement   1. M.S. Bars 2. b) HYSD bars   Structural Sections  Bitumen issued free  Bitumen issued at stipulated fixed price |  |  |